## Work Stream Status
Verizon Connect CDI
Individual Work Streams | PERCENT COMPLETE
Discovery and Analyze | 70%
Environment Setup | 0%
3rd Party Integration | 0%
TD -EDW Integration | 0%
Match and Survivorship | 0%
Enrich - Validation Integration | 0%
DataSteward UI Workflows | 0%
Reference Data | 0%
Publish Framework | 0%

## Environment Setup
WorkStream Status
Environment Setup
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Dev Environment in Teradata for MDM and ETL |  |  |  |  | Offshore Resource
0% | Test Environment in Teradata for MDM and ETL
0% | Dev Environment in Verizon for MDM | Chandra
0% | Test Environment for MDM in Verizon | Chandra
0% | Production Environment for MDM in Verizon | Chandra
0% | Dev Environment for ETL in Verizon
0% | Test Environment for ETL in Verizon
0% | Production Environment for ETL in Verizon
0% | GitHub Setup in Teradata and Verizon | Chandra and Ravi
0%
0%
0%
0% | Average % Complete

## Discovery-Analyze
WorkStream Status
Discovery and Analyze
% done | Module | Assigned To | Start Date | Expected By | Actual Completion | Notes
80% | End to End data flow - High Level integration architecture | Ravi and Team
90% | Data Modeling | Jean and Ravi |  |  |  | Customer, Vehicle, Device and ABC
90% | 3rd Party Source data Profiling | Chandra |  |  |  | 3rd Party Sources DDR, RDR, Conti, MBFT,Carnet, FDOK, Novero and Harmon
0% | EDW data profiling | Chandra and Ravi
90% | Source to Target Mapping for 3rd Party files | Karen and Chandra
90% | Source to Target Mapping for Teradata EDW | Karen and Chandra
90% | EDM Rules | Chandra |  |  |  | Validate, Enrich data coming from 3rd Party Data Sources.
30% | EDM Rules - EDW | Ravi and Chandra |  |  |  | Validate, Enrich data coming from Teradata EDW Sources.
0%
0%
70% | Average % Complete

## 3rd Party Integration
WorkStream Status
3rd Party Integration
% done | Phase | Assigned To | Start Date | Expected By | Actual Completion | Notes
0% | Pre - Stage Data Model creation for individual sources.
0% | RDR
0% | DDR
0% | MBFT
0% | FDOK
0% | Carnet
0% | Conti |  |  |  |  | One time load from Oracle DW
0% | Novero
0% | Harman
0% | NCOA |  |  |  |  | National Chane of Address data will be pre-loaded in pre stage and validated and loaded into Stage
0% | ACS |  |  |  |  | National Chane of Address data will be pre-loaded in pre stage and validated and loaded into Stage
0% | EDM Rules implementation |  |  |  |  | Business rules to validate and identify data.
0% | Data and Data Type Validations |  |  |  |  | This process will check for absolute duplicates. Data type mismatches
0% | Reference data setup needed for validatation or enrichment
0% | ABC Integration
0% | Pre - Stage to Stage Script creation and data loads
0% | Scheduling and error handling
0% | Data One full data loads into MDM |  |  |  |  | Daily do a full refresh of data one data into MDM. 4 files are provided daily to be loaded. This process will delete or archive and reload the data provided by Data one files into MDM area.
0% | Average % Complete

## TD - EDW Integration
WorkStream Status
Teradata EDW to MDM Stage Integration
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Scripts to load data from EDW to MDM Stage |  |  |  |  | TPT's and BTEQ scritps with the combination of views will be used to load net change data daily from Teradata EDW to MDM stage area.
0% | EDM Rules implementation
0% | Reference data setup needed for validatation or enrichment
0% | ABC Integration
0% | Scheduling and error handling
0% | TBD
0% | Average % Complete

## Match & Survivorship
WorkStream Status
Match and Survivorship
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Data Modeling to store match, survivorship and potential match results
0% | Matching Algorithm for Address matching
0% | Postal Address Match Profile
0% | Email Match Profile
0% | Phone Match Profile
0% | Vehicle Match Profile
0% | Device Match Profile
0% | Channel Match reconciliation |  |  |  |  | Postal, Email and Phone match reconciliation
0% | Matching Algorithm for Name matching
0% | Name Matching |  |  |  |  | Name matching integrated with Channel Reconciliation output
0% | Vehicle and Name Match Profile
0% | Potential Match Resolution Workflow
0% | Postal Survivorship
0% | Email Survivorship
0% | Phone Survivorship
0% | Customer Survivorship |  |  |  |  | Customer, Individual and Organization.
0% | Vehicle Survivorship
0% | Device Survivorship
0% | Customer Child Table Survivorship |  |  |  |  | Customer Address, Customer Program and other relation tables
0% | ABC Integration
0% | Customer, vehicle, device and Persona Customer assocications. |  |  |  |  | Customer Vehicle, Customer Account Device
0% | Stage to Transaction tables load |  |  |  |  | After matching and survivorship completed, load data from stage tables to transaction tables.
0% | End to End Workflow |  |  |  |  | Mtaching profiles, Reconciliation, Survivorship profiles
0% | Scheduling end to end workflow
0% | Data Modeling to store AcXiom and Customer relationship
0% | Postal Address Matching with AcXiom
0% | Email Address Matching with AcXiom
0% | Phone Matching with AcXiom
0% | Channel Match reconciliation
0% | Name Matching with Channel Reconciliation: AcXiom
0% | Survivorship to maintain MDM to AcXiom data crossreference |  |  |  |  | Weekly for steady state load
0% | Survivorship to maintain MDM to AcXiom data crossreference |  |  |  |  | Yearly twice for all the consumers who do not have AcXiom crossreference.
0% | Average % Complete

## Enrich- Validation Integration
WorkStream Status
Validate, Enrich data using third party or MDM modules
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Name Standardization |  |  |  |  | Reference data lookup for name standardization
0% | Phone Standardization |  |  |  |  | JUDF deployment and load data to stage
0% | Email Standardization |  |  |  |  | Validate Email syntax and enrich email domain names where it is required.
0% | Postal Address Validation and Standardization - Real Time |  |  |  |  | Integration with GDS for steady state loads using web services.
0% | Postal Address Validation and Standardization - Batch |  |  |  |  | Integration with GDS for one time load and quarterly or half yearly address standardizations.
0% | Vehicle Data Validation and Enrichment |  |  |  |  | Lookup and validate VIN number and enrich vehicle information on the basis of VIN.
0% | Views to be created to access AcXiom data
0%
0%
0% | Average % Complete

## DataSteward UI Workflows
WorkStream Status
Data Stward User Interface Workflows
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Potential Match Resolution for Customer |  |  |  |  | Match Resolution: New Customer or Merge to an existing Customer.
0% | Review and reload rejected data (associated with high frequency postal/email/phone channel data) |  |  |  |  | Data will be made available in Persona transaction and a handler to data steward would be available for review and reload or mark the row as an error. (When data is identified from Stage that this persona belongs to high frequecy then it would be marked as to be reviewed by a data setward, once reviewed data steward will take appropriate action whether to mark it as an error record or to be reloaded as master record).
0% | Dashboard for Data Loads |  |  |  |  | This UI workflows will showcase the data loads details from Source to Target
0%
0%
0%
0%
0%
0%
0% | Average % Complete

## Reference Data
WorkStream Status
Reference Data Setup and maintenance
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Code Set Maintenance and reference data UI workflow
0%
0%
0%
0%
0%
0%
0%
0%
0% | Average % Complete

## Publish Framework
WorkStream Status
Publish
% done | Phase | Assigned to | Start Date | Expected By | Actual Completion | Notes
0% | Views to publish or make master data and related data available
0%
0%
0%
0%
0%
0% | Average % Completion